## README
NORVELA PAY — RISK REGISTER WORKBOOK
This workbook has four sheets. Work them in order.
1. INHERITED-REGISTER | What you actually inherit on day one. 23 rows of near-useless entries. Your first exercise is to critique it — write down every structural defect you can find before you rebuild. There are at least twelve.
2. RISK-REGISTER-V2 | The rebuilt register. Columns are designed to survive an auditor, a supervisor and a board. Populate it from the dossier, the incident pack, the asset list and the vendor register.
3. SCORING-CRITERIA | Defined 1-5 scales for likelihood and impact. Without these, a 'High' rating is an opinion. With them, it is a finding.
4. RISK-APPETITE | Draft appetite statements derived from board behaviour. You will present these for approval in Phase 1.
TARGET: 35-45 well-formed risks. Fewer means you missed things; many more means you are logging findings as risks.
The difference between a FINDING and a RISK:
FINDING | A control that does not exist, or exists and does not work. Present tense. Has an owner and a fix date. Example: 'Service account credentials are not rotated.'
RISK | A future loss scenario with a cause, an event and a consequence. Has a likelihood and an impact. Example: 'Because service credentials are long-lived and stored in code, an attacker obtaining repository history could initiate unauthorised payouts, resulting in direct financial loss and supervisory action.'
One risk can be caused by many findings. Do not create one risk per finding — that is the most common way junior analysts produce a 200-row register that nobody reads.

## INHERITED-REGISTER
Risk ID | Risk | Owner | Likelihood | Impact | Mitigation | Status | Last updated
R-01 | Cyber attack | IT | High | High | Firewall in place | Open | 2025-04-02
R-02 | Data breach | IT | High | Medium | Encryption | Open | 2025-04-02
R-03 | Staff leaving | HR | Medium | Medium | Retention bonuses | Open | 2024-11-15
R-04 | Cloud outage | IT | Medium | High | AWS is reliable | Open | 2025-04-02
R-05 | GDPR fine | Legal | Low | High | We have a DPO | Open | 2024-06-01
R-06 | Fraud | Finance | Medium | High | Sentinel model | Open | 2025-04-02
R-07 | Regulatory change | Compliance | High | Medium | We monitor | Open | 2025-01-10
R-08 | Key person dependency | Ops | Medium | Medium | Documentation | Open | 2024-09-20
R-09 | Vendor failure | Procurement | Low | High | Contracts | Open | 2024-06-01
R-10 | Ransomware | IT | Medium | High | Backups | Open | 2025-04-02
R-11 | Insider threat | IT | Low | High | Background checks | Open | 2024-06-01
R-12 | DDoS | IT | Medium | Medium | Cloudflare | Closed | 2024-03-11
R-13 | Physical security | Facilities | Low | Low | Badge access | Open | 2023-12-01
R-14 | Phishing | IT | High | Medium | Training | Open | 2025-04-02
R-15 | Legacy systems | IT | High | Medium | Roadmap | Open | 2024-06-01
R-16 | Third party access | IT | Medium | High | VPN | Open | 2024-06-01
R-17 | Change failure | Eng | Medium | Medium | Testing | Open | 2025-04-02
R-18 | Backup failure | IT | Low | High | Tapes | Open | 2023-08-14
R-19 | AML breach | Compliance | Low | High | Screening | Open | 2025-04-02
R-20 | Licence withdrawal | Compliance | Low | High | Good relations | Open | 2024-06-01
R-21 | Model risk | Data | Medium | Medium | Monitoring | Open | 2025-04-02
R-22 | Concentration risk | Procurement | Medium | High | None | Open | 2025-04-02
R-23 | Skills shortage | HR | High | Low | Recruiting | Open | 2025-04-02

## RISK-REGISTER-V2
risk_id | risk_title | risk_statement (Cause -> Event -> Consequence) | risk_category | affected_asset_ids | affected_business_service | threat_source | vulnerability_exploited | risk_owner (named individual) | date_identified | inherent_likelihood (1-5) | inherent_impact (1-5) | inherent_score | existing_controls (control IDs) | control_effectiveness (E/PE/I/NT) | residual_likelihood (1-5) | residual_impact (1-5) | residual_score | within_appetite? (Y/N) | treatment_decision | treatment_actions | action_owner | target_date | status | annual_loss_expectancy_eur (FAIR) | regulatory_linkage (DORA/NIS2/GDPR/PCI/ISO/AI Act) | last_reviewed | next_review_due | evidence_reference

## SCORING-CRITERIA
LIKELIHOOD SCALE
Score | Label | Definition | Frequency guide
1 | Rare | Would require multiple independent control failures | Less than once in 10 years
2 | Unlikely | Possible but no known occurrence in the sector recently | Once in 5-10 years
3 | Possible | Has occurred at comparable firms; controls are partial | Once in 2-5 years
4 | Likely | Has occurred here or is occurring at peers regularly | Once or more per year
5 | Almost certain | Occurring now or control is absent entirely | Multiple times per year
IMPACT SCALE — score the HIGHEST applicable dimension
Score | Financial | Regulatory | Customer / operational | Reputational
1 | <€25k | Internal observation only | <10 merchants, <1h | No external awareness
2 | €25k-€100k | Supervisory query, informal | <100 merchants or <4h degradation | Customer complaints
3 | €100k-€500k | Formal supervisory finding requiring remediation plan | >100 merchants or payment outage <30min | Trade press coverage
4 | €500k-€2.5M | Enforcement action, fine, or public reprimand | Payment outage >30min or settlement error | National press, merchant churn
5 | >€2.5M | Licence condition, restriction or withdrawal | Sustained payment failure or unrecoverable settlement loss | Existential reputational damage
SCORE BANDS (Likelihood x Impact)
Band | Range | Governance requirement
Low | 1-4 | Risk owner manages. Annual review.
Moderate | 5-9 | Risk owner manages with documented treatment. Semi-annual review.
High | 10-15 | CRO oversight. Treatment plan with dates. Quarterly review. Reported to Risk Committee.
Critical | 16-25 | Board notification within 5 business days. Named executive owner. Monthly review until reduced.

## RISK-APPETITE
Risk category | Appetite level | Appetite statement | Tolerance threshold (breach trigger) | Escalation on breach
Regulatory & licence | Zero tolerance | No finding that could reasonably lead to a licence condition, restriction or withdrawal by Banco de Portugal. | Any Category 1 supervisory finding; any missed statutory notification deadline | Immediate CEO + Board notification
Settlement accuracy | Zero tolerance | No unreconciled settlement discrepancy persisting beyond one business day. | >1 business day unreconciled, OR any single discrepancy >€10,000 | CFO notification, incident raised
Confidentiality of customer data | Low | Accept residual risk only where the exposure window is <24h and affected records <1,000. | Any confirmed exposure >1,000 records OR any special-category data | DPO + CRO, Art.33 assessment within 24h
Availability — payment rails | Low | 99.95% monthly availability for PayRails and Vault. | <99.9% in any month, OR any single outage >30 min | CTO + COO, DORA incident assessment
Availability — non-payment features | Moderate | Accept degradation of reporting, portal and analytics features where payments are unaffected. | >4h outage of merchant portal | Product owner, no board escalation
Third-party concentration | Moderate (currently exceeded) | No single provider should support >60% of critical or important functions without a tested exit plan. | AWS currently at 100% — breach of appetite, board-accepted with time-bound remediation | Quarterly board reporting until remediated
Financial loss from fraud | Moderate | Annual fraud loss net of recovery below €750,000 (≈1.2% of revenue). | >€250,000 in any quarter | CFO + CRO review
Change failure | Moderate | Change failure rate below 5%; no change-induced payment outage. | Any change-induced payment incident | CTO review, CAB reinstatement considered